## Sprint1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story? | Notes
1 | As a super admin, I am able to CRUD admins | 3 | Youssef Shafei | N/A | N/A
2 | As an admin, I am able to CRUD partners | 3 | Youssef Sherif | N/A | N/A
3 | As an admin, I am able to CRUD life coaches | 3 | Ahmed Yasser | N/A | N/A
4 | As an admin, I am able to CRUD members | 3 | Farah hazem | N/A | N/A
5 | As a partner/admin, I am able to CRUD full time jobs | 3 | Philip Mouris | N/A | N/A
6 | As a member, I am able to read full time jobs | 0 |  | N/A | N/A | Repeated
7 | As an admin, I am able to CRUD job applications | 3 | Omar Nael | N/A | N/A
8 | As a member, I am able to create job applications | 0 |  | N/A | N/A | Repeated
9 | As a life coach/admin, I am able to CRUD slots in schedule | 3 | Youssef Samy | N/A | N/A
10 | As a member, I am able to read slots in life coaches' schedules | 0 |  | N/A | N/A | Repeated
11 | As a member/partner/life coach, I am able to CRUD my profile | 0 |  | N/A | N/A | Repeated
12 | As a partner/admin, I am able to CRUD reviews | 3 | Youssef Fathi | N/A | N/A
13 | As a member/admin, I am able to CRUD feedbacks | 3 | Abdellatif Emara | N/A | N/A
27