## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a user, I am able to view the header so that I am able to navigate the website | 3 | Omar Nael | Philip Mouris | Youssef Sherif
2 | As a user, I am able to view the footer so that I am able to navigate the website | 2 | Ahmed Yasser | Philip Mouris | Youssef Sherif
3 | As a user, I am able to sign up so that I am able to become part of Lirten Hub | 3 | Abdellatif | Philip Mouris | Youssef Sherif
4 | As a user, I am able to login so that I am able to acces Lirten Hub | 2 | Youssef Shafei | Philip Mouris | Youssef Sherif
5 | As a user, I am able to list all vacancies so that I am able to get an overview of vacancies | 5 | Philip Mouris | Youssef Abdelrahman | Youssef Sherif
6 | As a user, I am able to view a vacancy so that I am able to know its details | 3 | Youssef Abdelrahman | Philip Mouris | Youssef Sherif
7 | As a partner, I am able to submit a vacancy so that I am able to receive applications for them | 3 | Youssef Sami | Philip Mouris | Youssef Sherif
8 | As a user, I am able to search and sort vacancies so that I am able to get relevant vacancies | 5 | Youssef Sherif | Philip Mouris | Youssef Abdelrahman
9 | As a member, I am able to apply for vacancies so that I am able to get hired | 2 | Farah Hazem | Philip Mouris | Youssef Sherif
10 | As a member, I am able to view recommendations for vacancies so that I am able to get relevant vacancies (Backend) | 5 | Youssef Abdelrahman | Philip Mouris | Youssef Sherif