## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | As a user, I am able to list all life coaches so that I am able to view them | 3 | Youssef Sherif | Philip Mouris | Omar Nael
2 | As a user, I am able to view the profile of a life coach so that I am able to know his info | 5 | Philip Mouris | Omar Nael | Youssef Sherif
3 | As a life coach, I am able to edit my profile so that I am able to change my info | 2 | Youssef Fathi | Philip Mouris | Youssef Sherif
4 | As a user, I am able to list all partners so that I am able to view them | 3 | Youssef Sherif | Philip Mouris | Omar Nael
5 | As a user, I am able to view the profile of a partner so that I am able to know his info | 5 | Farah Hazem | Philip Mouris | Youssef Sherif
6 | As a partner, I am able to edit my profile so that I am able to change my info | 2 | Abdellatif | Philip Mouris | Youssef Sherif
7 | As a user, I am able to list all members so that I am able to view them | 3 | Youssef Sherif | Philip Mouris | Omar Nael
8 | As a partner, I am able to view my vacancies job applications so that I am able to accept or reject them | 5 | Youssef Samy | Philip Mouris | Youssef Sherif
9 | As a member, I am able to edit my profile so that I am able to change my info | 2 | Farah Hazem | Philip Mouris | Youssef Sherif
10 | As a member, I am able to submit a feedback to a partner so that I am able to assess him | 3 | Youssef Fathi | Philip Mouris | Youssef Sherif
11 | As a partner, I am able to submit a review to a member so that I am able to assess him | 3 | Youssef Fathi | Philip Mouris | Youssef Sherif
12 | As a life coach, I am able to post my slots so that members can reserve | 5 | Philip Mouris | Omar Nael | Youssef Sherif
13 | As a member, I am able to book a slot with a life coach so that I am able to meet him | 1 | Abdellatif | Philip Mouris | Youssef Sherif
14 | As a life coach, I am able to set a location of a slot so that I am able to meet a member | 2 | Omar Nael | Philip Mouris | Youssef Sherif
15 | As a life coach, I am able to confirm a slot so that I am able to meet a member | 1 | Omar Nael | Philip Mouris | Youssef Sherif
16 | As a partner, I am able to edit my vacancy so that I am able to change its info | 2 | Youssef Shafei | Philip Mouris | Youssef Sherif
17 | As an admin, I am able to approve a partner so that members can see him | 1 | Youssef Shafei | Philip Mouris | Youssef Sherif
18 | As an admin, I am able to approve a vacancy so that members can apply | 1 | Ahmed Yasser | Philip Mouris | Youssef Sherif
19 | As a super admin, I am able to create an admin so that he can manage the system | 2 | Ahmed Yasser | Philip Mouris | Youssef Sherif